PAWSIC QAPI Workshop

Skin Health & Wound Management  ·  A 60-Day Path to a Center of Excellence

YOUR GOAL Use this workshop to find opportunities to improve your wound program — and to achieve and maintain a level of Excellence. Over the next 60 days you will educate your team, assess your center, set targeted SMART goals, implement and track them, and earn your PAWSIC QAPI Certificate.

How this guide works.  The program runs in four phases across roughly 60 days. Work the 16 steps in order. Steps reference the toolkit you have already built — the Center Self-Assessment and the Monthly Sample Audit — plus the Wound Rounds Playbook, the Mobile Wound Group (MWG) Checklist, the CMS F686 Critical Element Pathway, and the online Wound Basics modules.

| PHASE 1 Set Up Steps 1–5 | PHASE 2 Assess & Build Steps 6–9 | PHASE 3 Implement & Track Steps 10–12 | PHASE 4 Certify & Sustain Steps 13–16 |
| --- | --- | --- | --- |

Start Here — Identify Your Skin Health Team Lead (SHTL)

Before the 60 days begin, name the person who will own this work: the Skin Health Team Lead (SHTL) of your Skin Health & Wound Management program. Look for these qualities:

| Licensed clinician | Primarily an RN or PT. |
| --- | --- |
| Wound expertise | Wound-certified, or actively pursuing wound certification. |
| Program oversight | Has oversight of the center’s entire wound program — not a single unit or shift. |
| Collaborative outcomes focus | Brings a strong, collaborative perspective and keeps the team aimed at patient outcomes. |

Consider two leads.  You may name two SHTLs to cover all or most shifts and to back each other up when issues arise (Note: only one SHTL per center will receive the 2 CEs and premium PAWSIC membership).

Register & share the code.  The SHTL will register under your facility name and receive a code that all clinical staff — to use to complete the Wound Basics modules.

Phase 1 — Set Up  (Steps 1–5)

| 1 | Identify & register your SHTL(s) Name your Skin Health Team Lead(s) and have them register under your facility name. Two leads are encouraged to cover most shifts and provide backup. |
| --- | --- |
| 2 | Complete Wound Basics & rally the staff The SHTL completes Wound Basics and, as center champion, ensures all clinical staff — NP, RN, LPN, PT, PTA, and RD — are registered and given the time allotted to complete the modules. |
| 3 | Run a weekly Wound Basics Debrief Gather staff weekly to discuss what they’re learning and the practice gaps they are noticing on the floor. |
| 4 | Download your toolkit The SHTL downloads the Center Self-Assessment, the Monthly Sample Audit, the Wound Rounds Playbook, and the CMS F686 Critical Element Pathway (CEP). → Center Self-Assessment · Monthly Audit · Wound Rounds Playbook · CMS CEP |
| 5 | Build a module schedule for the QAPI Blueprint from Assessment to Action moduels Review the content and timing, then set a pace — for example, a set number of modules per day — so the program completes within the 60-day window.In |

Phase 2 — Assess & Build  (Steps 6–9)

| 6 | Form the center wound team Work with the DON, Medical Director, NHA, and Director of Rehab to agree on a plan and create an engaged, center-based wound team spanning nursing, therapy, a provider, and CNAs. |
| --- | --- |
| 7 | Assess & set metrics with QAPI Meet with the center QAPI team to review the Center Self-Assessment tool and findings, then create metrics that align with your center, staffing, and priorities. → Center Self-Assessment |
| 8 | Workshop Wound Rounds (if selected) If wound rounds is a chosen goal, convene the wound team to “workshop” the Playbook and build or improve your rounds. Secure DON / NHA / Medical Director sign-off to support it. → Wound Rounds Playbook |
| 9 | Align your Mobile Wound Group (if needed) If you need an MWG, or your current group needs to better align, review the MWG Checklist with the DON / NHA and request a working meeting with the provider — use the checklist to navigate the discussion together. → MWG Checklist |

Phase 3 — Implement & Track  (Steps 10–12)

| 10 | Support implementation of your goals Put the agreed SMART goals into action alongside all center stakeholders (including residents/patients/resident council/family and staff, and the wound team. |
| --- | --- |
| 11 | Track progress with the Monthly Audit Use the Monthly Sample Audit to measure progress at the bedside, month over month. → Monthly Sample Audit |
| 12 | Report back to QAPI Share progress with the QAPI team — what worked, what didn’t — then revise the goals or plan and continue the improvement loop. |

Phase 4 — Certify & Sustain  (Steps 13–16)

| 13 | Attend the live PAWSIC QAPI Q&A Bring your questions to the live session for coaching and clarification. |
| --- | --- |
| 14 | Verify Wound Basics completions Work with PAWSIC to review and confirm your staff’s Wound Basics completions. |
| 15 | Earn your certificate Complete your post-test and print your Skin Health & Wound Management PAWSIC QAPI Certificate. |
| 16 | Join the community & keep going Join PAWSIC Special Interest Groups (SIGs) and Committees of interest and continue your journey. |

Your Toolkit at a Glance

Keep these close throughout the 60 days. All are confidential QI tools for your QAA/QAPI committee.

| Tool | What it’s for |
| --- | --- |
| Blueprint from Assessment - Action | 10 on-demand modules, each less than 10-15 min, designed as the foundational QAPI framework for the SHTL to complete, provides complete overview of the program, the toolkit, and goal setting for process improvement. |
| Center Self-Assessment | Annual deep-dive across five domains — patient-centered care, team, interventions, process, and infection control / EBP (F880). Sets your baseline and SMART goals. |
| Monthly Sample Audit | Focused 5-resident bedside check that validates the systems are working; tracks progress month over month. |
| Wound Rounds Playbook | Team guide to build functional, sustainable, patient-centered wound rounds. |
| Mobile Wound Group (MWG) Checklist | Guides selection of — or a realignment conversation with — your wound consultant / group. |
| CMS F686 Critical Element Pathway | Root-cause analysis for in-house and declining pressure injuries. |
| Wound Basics (online modules) | Foundational education completed by all clinical staff under your facility code. |

Aiming for Excellent. On the Center Self-Assessment, a score of 90–100% earns the designation Center of Skin Health Excellence. This 60-day workshop is how you get there — and how you stay there, quarter after quarter.